## Gantt Chart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | CAP STONE PROJECT - Team 2B |  |  |  |  | COMPANY NAME | [6 empty] | SHERIDAN COLLEGE
PROJECT MANAGER |  | TEAM |  |  |  |  | DATE | [6 empty] | 2018-06-05
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Data Gathering & Prep
1.1 | API & Live Data | Evans / Xian | 2018-03-12 | 2018-03-15 | 3 | 100% | bar: WEEK 1 F to WEEK 2 F
1.1.1 | Historical Data | Evans | 2018-03-15 | 2018-03-16 | 1 | 100% | bar: WEEK 2 W to WEEK 2 F
1.2 | Vision Pre-Processing | Yanan | 2018-03-15 | 2018-03-21 | 6 | 90% | bar: WEEK 2 W to WEEK 3 W
1.3 | Text Pre-Processing | Yanan | 2018-03-16 | 2018-03-22 | 6 | 40% | bar: WEEK 2 W to WEEK 3 R
2 | ML Model Creation
2.1 | Vision Brain (CNN) | Yanan / Afolabi | 2018-03-24 | 2018-03-28 | 4 | 22% | bar: WEEK 2 W to WEEK 2 F; WEEK 4 M to WEEK 4 R
2.2 | NLP Brain Dev | Yanan / Afolabi | 2018-03-29 | 2018-04-02 | 3 | 16% | bar: WEEK 2 W to WEEK 2 F; WEEK 4 F to WEEK 5 F
2.3 | Fusion Optimizer | Afolabi |  |  | 0 | 20% | bar: WEEK 2 W to WEEK 2 F
2.4 | Hyperparameter Tuning | Afolabi |  |  | 0 | 10% | bar: WEEK 2 W to WEEK 2 F
3 | Backend System
3.1 | Env Configuration | Evans |  |  | 0 | 0% | bar: WEEK 2 W to WEEK 2 F
3.2 | Async Automation | Xian |  |  | 0 | 0% | bar: WEEK 2 W to WEEK 2 F
3.2.1 | Containerization | Xian |  |  | 0 | 0% | bar: WEEK 2 W to WEEK 2 F
4 | Frontend Application
4.1 | UI/UX Wireframing | Evans |  |  | 0 | 0% | bar: WEEK 2 W to WEEK 2 F
4.2 | HTML, CSS, Javascript | Evans |  |  | 0 | 0% | bar: WEEK 2 W to WEEK 2 F
4.3 | Map Integration | Evans |  |  | 0 | 0% | bar: WEEK 2 W to WEEK 2 F
4.4 | Testing & Polish | Team |  |  | 0 | 0% | bar: WEEK 2 W to WEEK 2 F