## Smart-Shield AI Project Gantt C
WBS | Task Description | Owner | Start | Due | W5-6 | W7-8 | W9-10 | W11-12 | W13-14
WP1 | Data Gathering & Prep | Evans / Xian | W5 | W6 | █
1.1 | API & Live Data | Evans / Xian | W5 | W5 | █
1.2 | Historical Data | Evans | W5 | W6 | █
1.3 | Vision Pre-Processing | Yanan | W6 | W6 | █
1.4 | Text Pre-Processing | Yanan | W6 | W6 | █
WP2 | ML Model Creation | Yanan / Afolabi | W7 | W10 |  | █ | █
2.1 | Vision Brain (CNN) | Yanan / Afolabi | W7 | W8 |  | █
2.2 | NLP Brain Dev | Yanan / Afolabi | W7 | W8 |  | █
2.3 | Fusion Optimizer | Afolabi | W9 | W9 |  |  | █
2.4 | Hyperparameter Tuning | Afolabi | W10 | W10 |  |  | █
WP3 | Backend System | Xian / Evans/Yanan | W9 | W12 |  |  | █ | █
3.1 | Env Configuration | Evans | W5 | W5 | █
3.2 | Async Automation | Xian | W9 | W10 |  |  | █
3.3 | Containerization | Xian | W11 | W12 |  |  |  | █
WP4 | Frontend Application | Evans | W11 | W14 |  |  |  | █ | █
4.1 | UI/UX Wireframing | Evans | W11 | W11 |  |  |  | █
4.2 | HTML, CSS, Javascript | Evans | W11 | W12 |  |  |  | █
4.3 | Map Integration | Evans | W12 | W12 |  |  |  | █
QA | Testing & Polish | Team | W13 | W14 |  |  |  |  | █

## Sheet1
WBS | Task Description | Owner | Start | Due | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14
WP1 | Data Gathering & Prep | Evans / Xian | W5 | W6 | █ | █
1.1 | API & Live Data | Evans / Xian | W5 | W5 | █ | █
1.2 | Historical Data | Evans | W5 | W6 | █ | █
1.3 | Vision Pre-Processing | Yanan | W6 | W6 | █ | █
1.4 | Text Pre-Processing | Yanan | W6 | W6 | █ | █
WP2 | ML Model Creation | Yanan / Afolabi | W7 | W10 |  |  | █ | █ | █ | █
2.1 | Vision Brain (CNN) | Yanan / Afolabi | W7 | W8 |  |  | █ | █
2.2 | NLP Brain Dev | Yanan / Afolabi | W7 | W8 |  |  | █ | █
2.3 | Fusion Optimizer | Afolabi | W9 | W9 |  |  |  |  | █ | █
2.4 | Hyperparameter Tuning | Afolabi | W10 | W10 |  |  |  |  | █ | █
WP3 | Backend System | Xian / Evans/Yanan | W9 | W12 |  |  |  |  | █ | █ | █ | █
3.1 | Env Configuration | Evans | W5 | W5 | █ | █
3.2 | Async Automation | Xian | W9 | W10 |  |  |  |  | █ | █
3.3 | Containerization | Xian | W11 | W12 | [6 empty] | █ | █
WP4 | Frontend Application | Evans | W11 | W14 | [6 empty] | █ | █ | █ | █
4.1 | UI/UX Wireframing | Evans | W11 | W11 | [6 empty] | █ | █
4.2 | HTML, CSS, Javascript | Evans | W11 | W12 | [6 empty] | █ | █
4.3 | Map Integration | Evans | W12 | W12 | [6 empty] | █ | █
QA | Testing & Polish | Team | W13 | W14 | [8 empty] | █ | █